## Instructions for LowModerateHig
Work Breakdown Structure - Instructions & Guidance | Resources
Please read all instructions in detail prior to filling out this spreadsheet Once partnership has been established between an agency and cloud service provider for an initial FedRAMP Authorization, the agency should send over an In Process Request (IPR) (see cell F3 for a link to a template) and the CSP and agency should convene to complete this work breakdown structure template along with the 3PAO. On the CSP/Agency Information tab, please fill out the ask for information. Additionally, if your system is a Low, Moderate, or High system, please complete Low/Moderate/High WBS tab, then rename the tab to your corresponding impact level, and delete the Li-SaaS WBS tab. If you are a Li-SaaS system, please use the Li-SaaS WBS tab and delete the Low/Moderate/High WBS tab. The agency and CSP should ensure they are working together to develop an agreed upon project schedule. General Guidance - CSPs and agencies should be as precise as possible with estimations. - Please include a start and end date for each activity - If dates shift, please keep all relevant parties informed - The timelines can happen in parallel, you can work with an agency prior to Kickoffs and SAR Debriefs to ensure progress is made. You do not need to wait for a Kickoff or SAR Debrief to continue working on/reviewing the package Section 1: Design / Build System 1.1: List any gaps that need to be addressed and identify dates for remediation to meet federal mandates and FedRAMP requirements. Section 3: Develop and Finalize SSP 3.4: When the CSP and Agency are ready for a kickoff meeting, the CSP should develop a kickoff briefing. Please use the PMO's template to develop a kickoff presentation (see cell F21 for a link to a template). Section 4: Develop and Finalize SAP - End date should be date of finalized SAP Section 5: Develop and Finalize SAR / POA&M 5.1: List the start and end dates of the full 3PAO assessment. 5.3: Please provide an estimated period for final SAR delivery. 5.5: Once a final SAR delivery date has been identified, the PMO suggests allowing the agency about 2 weeks to review the SAR before convening for a SAR debrief. Section 6: Final Agency Review and ATO 6.1: List the estimated review period the agency will require before briefing the Authorizing Official. 6.2: Provide an estimated period for AO review and approval 6.3: Provide the period within which the CSP and PMO can expect to receive an ATO. Send a copy of the ATO letter to ato-letter@fedramp.gov. Section 7: 7.1: Providing an ATO Letter (see cell F29 for a link to a template) to ato-letter@fedramp.gov triggers the PMO's final review of the package. The CSP should upload the SSP and POA&M. The 3PAO should upload the SAP and SAR. Use the PMO's Initial Package Upload Checklist (see cell F33 for a link) to ensure all documentation is uploaded to the proper areas within OMB MAX. 7.2: The PMO's review is conducted from the perspective of governmentwide reuse. Once you submit all final deliverables to the PMO, the review team will inform you about the current timeline before they begin reviewing your package. See cell F36 for a link to a sample review report.
In-Process Request Template
Kickoff Template
SAR Debrief Template
ATO Letter Template
Initial Authorization Upload Checklist

## Instructions for Li-SaaS WBS
Work Breakdown Structure - Instructions & Guidance | Resources
Please read all instructions in detail prior to filling out this spreadsheet Once partnership has been established between an agency and cloud service provider (CSP) for an initial FedRAMP Authorization, the agency should send over an In Process Request (IPR) (see cell F3 for a link to a template) and the CSP and agency should convene to complete this work breakdown structure template along with the 3PAO. Note: the PMO requires submission of a completed WBS before scheduling a Kickoff Meeting, and is a requirement to be listed as 'In Process' on the FedRAMP Marketplace. On the CSP/Agency Information tab, please fill out the ask for information. Additionally, since this is a LI-SaaS system, delete the LowModerateHigh WBS tab. The agency and CSP should ensure they are working together to develop an agreed upon project schedule. General Guidance - CSPs and agencies should be as precise as possible with estimations. - Please include a start and end date for each activity - If dates shift, please inform the PMO and provide an updated WBS - The timelines can happen in parallel, you can work with an agency prior to Kickoffs to ensure progress is made. You do not need to wait for a Kickoff to continue working on/reviewing the package Section 1: Design / Build System 1.1: List any gaps that need to be addressed and identify dates for remediation to meet federal mandates and FedRAMP requirements. Section 3: Develop and Finalize Architecture, Appendix B and E (Rev. 4) or SSP with Appendix A (Rev. 5) 3.1 CSP engages 3PAO to perform upcoming assessment to begin once Agency approves Architecture 3.2 CSP notifies PMO that Documents are completed and PMO sets up Connect.gov portal for vendor (if applicable) 3.3 Documentation Finalized and Uploaded to Connect.gov. Notify sponsor Agency and FedRAMP PMO Section 4: Kickoff Presentation 4.5: When the CSP and Agency are ready for a kickoff meeting, the CSP should develop a kickoff briefing. Please use the PMO's template to develop a kickoff presentation (see cell F21 for a link to a template). Section 7: Final Agency Review and ATO 7.1: List the estimated review period the agency will require before briefing the Authorizing Official. 7.2: Provide an estimated period for AO review and approval 7.3: Provide the period within which the CSP and PMO can expect to receive an ATO. Send a copy of the ATO letter to info@FedRAMP.gov. Section 8: 8.1: Providing an ATO Letter (see cell F29 for a link to a template) to ato-letter@fedramp.gov triggers the PMO's final review of the package. The CSP should upload the Appendix B and E (Rev. 4) or SSP with Appendix A (Rev. 5) with Attachments to OMB Max. 8.2: The PMO's review is conducted from the perspective of governmentwide reuse. Once you submit all final deliverables to the PMO, the review team will inform you about the current timeline before they begin reviewing your package. See cell F36 for a link to a sample review report.
In-Process Request Template
Kickoff Template
ATO Letter Template
Initial Authorization Upload Checklist
Sample Review Report

## CSPAgency Information
Contact List/Signatures Page
Cloud Service Provider: | CSP Contacts | Title | Email | Phone | Secure Repository Access Needed (Y/N)
Cloud Service Offering: | Name of POC 1 | Generic Contact (e.g. fedramp@cspname.com) |  |  |  | CSPs: please include the contact information of those who will be directly managing the development and management of your system's security package for FedRAMP Authorization.
FedRAMP ID: | Name of POC 2 | Primary Contact
FedRAMP Baseline: | Name of POC 3 | Sales Contact
| Name of POC 4 | Security Contact
Name of POC 5
Authorizing Agency: | Agency Contacts | Title | Email | Phone | Secure Repository Access Needed (Y/N) | Agencies: please include the contact information of those from your agency's cybesecurity/IT team who will be directly managing the review of the cloud offering's security package for an ATO.
Agency Authorizing Official: | Name of POC 1 | Agency Liaison
| Name of POC 2 | Primary ISSO
| Name of POC 3 | Project Owner
| Name of POC 4 | Business Owner
| Name of POC 5 | Authorizing Official
| 3PAO Contacts | Title | Email | Phone | Secure Repository Access Needed (Y/N) | CSPs/3PAOs: please include the contact information of those from your assessing 3PAO team who will be directly assessing your system and will be the main POCs throughout this effort. These individuals will be included in PMO meeting (Kickoffs, SAR Debriefs, etc.)
Signatures | Name of POC 1
The two signatures below indicate that both the agency and the Cloud Service Provider have reviewed and approved this document. The PMO will not consider a WBS valid unless there are signatures from an individual from both parties. Please type the name of the individual that is signing off on this document in cells B22 and B23. | Name of POC 2
Authorizing Agency Signature: | Name of POC 3
Cloud Service Provider Signature: | Name of POC 4
Name of POC 5
Note on E3: Do not insert the title of the employee (ie. CTO). Instead, place what their title is considered in this authorization effort. ======
Note on E11: These are suggested contacts, however an agency may not have all of these contacts. Rename them as you see fit. ======

## LowModerateHigh WBS
Task # | Task | Responsibility | Start Date | End Date | Notes / Resources / Questions
1 | Design/Build System |  |  |  | System should already be operational; CSP should list any gaps and identify dates for remediation to meet federal mandates and FedRAMP requirements
1.1 | Remediate Gaps (CSP should insert any identified gaps and timelines associated with remediation below) | CSP
1.1.1 | <Gap 1> | CSP |  |  | CSP insert gaps here; add lines if needed
1.1.2 | <Gap 2> | CSP
2 | Establish Partnership with an Agency
2.1 | Agency Provides an In-Process Request to the PMO to indicate partnership establishment | Agency |  |  | In-Process Request Template
2.2 | CSP/Agency to provide a completed WBS to FedRAMP PMO | Agency, CSP
3 | Develop and Finalize SSP |  |  |  | End date should be date of finalized SSP
3.1 | Develop SSP and Deliver to Agency | CSP
3.2 | Review draft SSP | Agency
3.3 | Prepare Kick-off Presentation | CSP |  |  | *CSP uploads kickoff briefing to their secure repository to allow for PMO review and feedback prior to scheduling the kickoff meeting. Please notify the PMO via intake@fedramp.gov once your deck is uploaded.
3.4 | Hold Kickoff Meeting | CSP, Agency, 3PAO (optional) |  |  | *Agency should invite POCs who will be reviewing the security package and making a risk recommendation to the AO for Authorization. *This meeting should be scheduled during a time frame that works best for the agency, and should allow enough time for agency personnel to review all relevant information prior to the meeting.
3.5 | CSP listed as In-Process on FedRAMP Marketplace* |  |  |  | *This is contingent on the CSP meeting all criteria outlined in our Marketplace Guidance, as well as the Agency team consenting to the listing. Additionally, your 3PAO assessment must begin within 6 months of your In-Process date.
3.6 | Remediate draft SSP based on Agency feedback | CSP
3.7 | Validate CSP remediation | Agency
3.8 | Document awareness of Customer Responsibilities | Agency
3.9 | Approve SSP | Agency
4 | Develop and Finalize SAP |  |  |  | End date should be date of finalized SAP
4.1 | Develop draft SAP and Deliver to Agency | CSP, 3PAO
4.2 | Review SAP and provide comments | Agency
4.3 | Remediate draft SAP comments | CSP, 3PAO
4.4 | Validate SAP remediations | Agency
4.5 | Approve SAP | Agency
5 | Develop and Finalize SAR / POA&M
5.1 | Conduct Security Assessment | 3PAO |  |  | Start date must occur within 6 months of In Process designation date. NOTE: if your security assessment is set to begin or end before a Kickoff Meeting with the PMO can be held, please reach out directly to the PMO for instructions on scheduling a Combined KO/SAR Debrief.
5.2 | Remediate Risks | CSP
5.3 | Finalize and deliver SAR | 3PAO
5.4 | Develop and deliver POA&M | CSP
5.5 | Prepare SAR Debrief Presentation | CSP, 3PAO |  |  | *Provide draft SAR debrief presentation to the FedRAMP PMO for review and feedback prior to scheduling the SAR debrief. Ensure you upload the presentation to a secure repository and notify the PMO via intake@fedramp.gov.
5.6 | Hold SAR Debrief | CSP, 3PAO, Agency |  |  | Formal meeting with Agency, 3PAO, and CSP
5.7 | Review & Approve SAR | Agency
6 | Final Agency Review and ATO |  |  |  | The agency partner should fill out this section entirely. This section must be completed to be considered complete for PMO scheduling purposes.
6.1 | Complete review of authorization package | Agency
6.2 | Submit authorization package to Agency AO for final approval | Agency
6.3 | Issue ATO and provide copy to FedRAMP via info@fedramp.gov | Agency |  |  | *End date should be within 1 year of In Process designation date
6.4 | Upload all required security package material to the secure repository | Agency |  |  | CSPs should use the Initial Authorization Upload Checklist
7 | FedRAMP PMO Review and FedRAMP Authorized Decision (for awareness, do not fill out) |  |  |  | Please leave this portion blank, the PMOs review is dependent on how many packages are in our queue. Once an ATO is submitted, the PMO will provide estimates for the review timeline.
7.1 | Review package and release an Agency Package Review Report | PMO |  |  | FedRAMP is committed to a package review within 10 days upon start of review; CSP package is put in queue according to order received
7.2 | Remediate PMO findings and deliver updates to PMO | CSP, 3PAO |  |  | This timeline will vary depending on FedRAMP PMO findings
7.3 | Inform CSP that FedRAMP Authorization designation has been achieved | PMO
7.4 | Marketplace listing for CSO is updated to reflect FedRAMP Authorized and date of authorization | PMO

## Li-SaaS WBS
Task # | Task | Responsibility | Start Date | End Date | Notes / Questions
1 | Design/Build System |  |  |  | System should already be operational; CSP should list any gaps and identify dates for remediation to meet federal mandates and FedRAMP requirements
1.1 | Remediate Gaps (CSP should insert any identified gaps and timelines associated with remediation below) | CSP
1.1.1 | <Gap 1> | CSP |  |  | CSP insert gaps here; add lines if needed
1.1.2 | <Gap 2> | CSP
2 | Establish Partnership with an Agency
2.1 | Agency Provides an In-Process Request to the PMO to indicate partnership establishment | Agency |  |  | In-Process Request Template
2.2 | CSP/Agency to provide a completed WBS to FedRAMP PMO | Agency, CSP
3 | Develop and Finalize Architecture, Appendix B and E (Rev. 4) or SSP with Appendix A (Rev. 5)
3.1 | Engage 3PAO to perform upcoming assessment to begin once Agency approves Architecture | CSP
3.2 | CSP notifies PMO that Documents are completed and PMO sets up OMB MAX portal for vendor | CSP
3.3 | Documentation Finalized and Uploaded to OMB MAX. Notify sponsor Agency and FedRAMP PMO | CSP
4 | Agency Review and Approval of Architecture and Documents
4.1 | Agency reviewed draft | Agency
4.2 | CSP remediates draft documents | CSP
4.3 | Agency approves architecture and documents and recommends Kick-off Presentation | Agency
4.4 | Assessment can begin | 3PAO
4.5 | Prepare Kick-off Presentation | CSP |  |  | *CSP uploads kickoff briefing to their secure repository to allow for PMO review and feedback prior to scheduling the kickoff meeting. Please notify the PMO via intake@fedramp.gov once your deck is uploaded.
5 | Kick-Off Presentation by CSP
5.1 | Vendor Presents Architecture, security issues and schedule | CSP
5.2 | Agency concurs on In-Process | Agency
5.3 | Update FedRAMP Marketplace to indicate In-Process | PMO
6 | Assessment
6.1 | Perform Assessment | 3PAO
6.2 | Remediate Risks | CSP
6.3 | Finalize and deliver Authorization Documents | 3PAO
6.4 | Develop and deliver POA&M | CSP
7 | Final Agency Review and ATO
7.1 | Complete review of authorization package | Agency
7.2 | Submit authorization package to Agency AO for final approval | Agency
7.3 | Issue ATO and provide copy to FedRAMP via info@fedramp.gov | Agency |  |  | *End date should be within 1 year of In Process designation date
7.4 | Upload all required security package material to secure repository | Agency |  |  | CSPs should use the FedRAMP Initial Authorization Package Checklist
8 | FedRAMP PMO Review and FedRAMP Authorized Decision (for awareness, do not fill out) |  |  |  | Please leave this portion blank, the PMOs review is dependent on how many packages are in our queue. Once an ATO is submitted, the PMO will provide estimates for the review timeline.
8.1 | Review package and release an Agency Package Review Report | PMO |  |  | FedRAMP is committed to a package review within 10 days upon start of review; CSP package is put in queue according to order received
8.3 | Remediate PMO findings and deliver updates to PMO | CSP, 3PAO |  |  | This timeline will vary depending on FedRAMP PMO findings
8.4 | Inform CSP that FedRAMP Authorization designation has been achieved | PMO
8.5 | Marketplace listing for CSO is updated to reflect FedRAMP Authorized and date of authorization | PMO